## Slide 1: Twinning project ENEA – ENforcing Environmental Acquis
César Seoánez
Skopje, 29th of April, 2015
1st Steering Committee

## Slide 2: OUTLINE
1st quarter assessment (12 January – 11 April 2015)
Addendum 1
Inception Report
Programme for next 6 months (12 April – 11 October 2015)
Operative Side Letter 2
Quarterly Report 1

## Slide 3: Coordination
Initial meetings: SEI, MoEPP, ZELS, MoLSG, local inspectors, industries, CFCD, DEU
Info exchange with:
Twinning Air Quality (not yet started)
Twinning IED (not yet started)
TA Project Water Management
1st QUARTER:
Coordination with TA project supporting local level

## Slide 4: Communication
Website: www.sei.gov.mk
Training on Twinning + monitoring visit
1st QUARTER:
Other visibility materials: leaflet, notebooks, folder, pen, mug, banner
Questionnaire
Bitola University

## Slide 5: Progress vs. Work Plan
1st QUARTER:

## Slide 6: Progress vs. Work Plan
1st QUARTER:
Good (delay in Kick-off requested by BC)

## Slide 7: Activities
1st QUARTER:
February
January (starting 12th )
1.1, mission 1 (institutional assessment)
Arrival RTA, selection of assistants
Initial meetings with MoEPP, ZELS, CFCD, DEU
Discussion with SEI key staff about their needs & definition of work plan
Website
Further meetings with inspectors & other stakeholders

## Slide 8: Activities
1st QUARTER:
March
2.1, mission 1: legal assessment
2.2, mission 1: review related to inspection planning & reporting
2.1, mission 2: legal assessment & discussion of new Law for Insp. on Env.
Delivery of Addendum 1
1.1, mission 2 (institutional assessment)

## Slide 9: Activities
1st QUARTER:
Main outputs
Legal assessment
Inception Report – Addendum 1
Institutional assessment
SEI website & project leaflet
April (ending 11th )
Preparation missions April – May: Side Letter 3
Start drafting Inception Report
Preparation visibility materials
Preparation Kick-off

## Slide 10: Activities
1st QUARTER:
Other outputs
Translation into English of parts of existing legislation relevant for env. inspection
Translation into English of Law on Inspection Supervision

## Slide 11: Participation BC experts
1st QUARTER:
52 BC participants in meetings held in missions
Excluding initial meetings held in January - February

## Slide 12: Expenditures
1st QUARTER:
In 1st quarter ~ 6.87 % of activities’ budget
As planned
Savings in flight tickets

## Slide 13: QUARTERLY REPORT
Project challenges addressed in Addendum 1
Essential to endorse as fast as possible Addendum 1

## Slide 14: PROGRAMME NEXT 6 MONTHS
May
Activity 1.2, mission 2: Start drafting inspection manual
Activity 1.1, mission 4: Drafting proposals for institutional improvement
April (starting 12th )
Steering Committe 1
Kick-off event (act. 0.1)
Activity 1.2, mission 1: analysis of existing docs, planning of docs to deliver
Activity 1.1, mission 3: workshops to discuss with stakeholders
Quarterly Report 1, Operative Side Letter 2, Inception Report

## Slide 15: PROGRAMME NEXT 6 MONTHS
June
Activity 1.1, mission 5: Final version of proposals for institutional improvement
Activity 1.3, mission 1: Training Needs Assessment
Activity 2.2, mission 3: Adoption of RMCEI
Activity 2.1, mission 3: Support in elaboration of new Law for Insp. on Env.
May
Activity 1.4, mission 1: Study visit to Galicia (Spain)
Activity 2.2, mission 2: Updates to legislation related to planning & reporting

## Slide 16: PROGRAMME NEXT 6 MONTHS
August
Activity 2: Rest a bit
Activity 1: Enjoy life
July
Steering Committe 2: 30th July
Activity 1.2, mission 4: 3rd (and last) mission to draft manual inspections
Activity 1.2, mission 9: 1st mission to draft BAT guidance
Activity 1.2, mission 3: 2nd mission to draft manual inspections
Quarterly Report 2, Operative Side Letter 3
Activity 2.1, mission 5: risk matrix-based approach to plan inspections

## Slide 17: PROGRAMME NEXT 6 MONTHS
October (until 11th )
No mission
September
Activity 1.4, mission 2: study tour to Portugal
Activity 2.2, mission 4: training curricula for RMCEI implementation
Activity 1.2, mission 5: 1st mission to draft check lists waste
Activity 1.3, mission 2: training programme & start drafting materials
Activity 3.1, mission 1: Analysis of BPMS
Activity 2.1, mission 4: finalise proposals for new Law for Insp. on Env.

## Slide 18: OPERATIVE SIDE LETTER 2
If no objections to contents, time for approval?
Slight change: delete from mission 1.2.7 names of experts

## Slide 19: ADDENDUM 1: Changes since version 15th April
Main text: Cumulative amount (due to corrigendum SL2)
Annex 3 (explanatory note):
Correction of amounts stated for translation/interpretation
Dimitris Tsotsos is included in activities 1.2 and 1.3
Rob Kramers is assigned as Component Leader of Component 2
Annex 2 (original & amended text):
Dimitris Tsotsos is included in activities 1.2 and 1.3
B.1.1.7 : Draft proposals for structure and contents, not Twinning Fiches
Rob Kramers is assigned as Component Leader of Component 2
B.1.1.7 : Draft proposals for structure and contents, not Twinning Fiches

## Slide 20: INCEPTION REPORT
Agreed by Partners
Calendar in A3
In line with Addendum 1
Highlights:
Act. 1.2: industrial activities  factsheets + list of issues to inspect
Act. 1.2: inspection manual integrating IPPC/BAT guidelines + check lists
Act. 1.1: mission 1.1.6, proposals for new projects
Act. 1.2: will take into account materials from previous Twinning on Waste

## Slide 21: INCEPTION REPORT
Highlights:
Act. 3.1: BPMS & IRAM
Act. 2.2: RMCEI + IED art. 23
Act. 1.3: train the trainer

## Slide 22
Thank you very much !
Благодарам многу!
blinkov_d@yahoo.com
inspection.cs@gmail.com
www.sei.org.mk