## Slide 1: Twinning project ENEA – ENforcing Environmental Acquis
César Seoánez
Skopje, 21st of July, 2016
6th Steering Committee

## Slide 2: OUTLINE
6th quarter assessment (12 April – 11 July 2016)
Programme until end of implementation (12 July – 11 August 2016)
Quarterly Report 6
Operative Side Letter 7
Outputs delivered to Steering Committee

## Slide 3: Coordination
Meetings: multiple, within missions, with stakeholders, specially inspectors
Participation in Steering Committee, providing suggestions on project extension
6th QUARTER:
Coordination with Twinning IED
Participation of its Team Leader in training; discussion about networking
Participation in Steering Committees & closure event
Info about outputs, incl. English translation of updated draft Law for Ins. on Env. shared
Coordination with TA project supporting local level
Several meetings with Inspection Council & activities with & for them
Info on QR5 sent to DG NEAR & DG Environment

## Slide 4: Communication
Website: www.sei.gov.mk
News in Macedonian media:
Press conference in Economic Chamber, 11/07/2016
6th QUARTER:
TV channel Nova on the 10/05/2016 (training in Gevgelija)
Info event about EU funding possibilities for Inspectorates, 07/07/2016
Printing of updated leaflet, Waste Watch, insp. manual & factsheets
Macedonian TV and written media on the 31/05/2016 (training in Prilep)
All supporting materials, incl. Waste Watch, Guidance on Sampling, updated leaflet
Second youtube video by FIIAPP including interviews to beneficiaries
Drafting of article for American Chamber of Commerce in Macedonia

## Slide 5: Progress vs. Work Plan
6th QUARTER:

## Slide 6: Progress vs. Work Plan
Good
6th QUARTER:

## Slide 7: Activities
6th QUARTER:
April (starting 12th )
Activity 2.2, mission 6: training based on inspection to pilot installation (region 3)
Activity 1.3, mission 7: 3 one-day trainings on comm. skills & team building
Activity 3.1, mission 3: training on use of IRAM software
Steering Committee 5: 22nd April

## Slide 8: Activities
6th QUARTER:
Letter from SEA supporting draft Law and recommending adoption
May
Activity 2.2, mission 7: training based on inspection to pilot installation (region 2)
Activity 1.3, mission 8: 3 one-day trainings on comm. skills & team building
Activity 3.1, mission 3: further work on BPMS
Updated project’s brochure

## Slide 9: Activities
6th QUARTER:
July (until 11th )
Info session on EU funding possibilities for Inspectorates
Activity 2.1, mission 4.b: Meeting between Dutch & Macedonian Inspection Councils
June
Activity 2.1, mission 9: first training on sampling & monitoring
Activity 2.2, mission 8: training based on inspection to pilot installation (region 4)
Press conference in Economic Chamber
Activity 2.1, mission 10: second training on sampling & monitoring

## Slide 10: Activities
Main outputs
MK translation of Chapter 5 (BAT Conclusions) BREF for pig & poultry farms
SEI - Twinning website & updated brochure
Small guidance for sampling & control of self-monitoring reports
Waste Watch booklet for control of waste shipments
6th QUARTER:
Updated assessment and recom. for sustainability & next upgrades of BPMS
ALB translation of inspection manual
MK translation of Chapter 5 (BATs) BREF for management of tailings and waste-rock in mining
Trainings on skills, sampling & monitoring, and pilot inspections

## Slide 11: Activities
6th QUARTER:
Other outputs
Article in magazine of American Chamber of Commerce in Macedonia
Info session for Inspectorates
Press conference in Economic Chamber

## Slide 12: Participation BC experts
295 BC participants in meetings/trainings held in missions
High participation, with high number from local level
6th QUARTER:

## Slide 13: Expenditures
In 6th quarter ~ 15.2 % of activities’ budget
As planned
Savings in flight tickets
6th QUARTER:

## Slide 14: QUARTERLY REPORT
Draft Law  prepare to send to Government in August
Inspection Council should address Twinning docs sent,
to align to EU best practices (review of LoIS starts Sept.)
Tool to absorb, update and promote the use of outputs of project
Inventory of installations: collect & compile data
Managers in SEI, MoEPP, CFCD, DEU & SEA should continue pushing for a change in Law for Insp. Supervision
Create Network of Environmental Inspectors
Overload in planning & reporting, evaluation of inspectors with financial penalties...
Wrap-up: contact list, DVD copies with all materials...

## Slide 15: PROGRAMME UNTIL END
July (starting 12th)
Activity 1.3, mission 9: four 1-day workshops to close training programme
August(until 11th)
Closure of project, final reporting
Activity 1.1, mission 6: follow-up projects
Steering Committee 6: 21st July
Closure event: 20th July
Activity 3.1, mission 4: final mission BPMS
Work to set up basis for Network of Environmental Inspectors

## Slide 16: OPERATIVE SIDE LETTER 7
Builds upon side letter 12
Explicit approval of OSL is very welcome

## Slide 17: COMMENTS TO OUTPUTS DELIVERED TO ST.C.?
3.1.3.b – SEI’s BPMS updated assessment & proposals for next steps
1.2.12 – final version of inspection manual in ALB
2.1.9 – 2.1.10: Brief guidance on sampling & control of self-monitoring reports
1.2.6 – Waste Watch booklet
2.1.4.b – Report on meeting between Dutch & Macedonian Inspection Councils

## Slide 18
Thank you very much !
Благодарам многу!
blinkov_d@yahoo.com
inspection.cs@gmail.com
www.sei.gov.mk